## Sheet2
MCI Project Weekly Time Sheet
Team | 17 | Student ID | a1820323 |  |  | Week starting: | 2022-04-04
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-04-04 | 16:00 | 19:00 | 3 | Revied the draft of business case and draft plan | All team members reviewed all part of this project and gave some feedbacks of each other.It helps team members to understand more about this project. | We have some Improvements based on the team members feeback.
Tuesday | 2022-04-05 | 12:00 | 16:00 | 4 | Finished the business draft plan and set the database pipeline to store stock index and stock info. | Submitted the business draft and draft plan, check the project progress for the next client meeting. | Business case and draft plan were finished. Some indexs were stored in the database.
Wednesday | 2022-04-06 | 15:00 | 18:00 | 3 | Weekly meeting[10th/2022] | Check the team member's progress,and we set weekly goals of each colleges we expected to be completed.Help each other if anyone needs help | We reviewed code together and explained the functions, we also did some research about the stock API. And each members understood that:stock index and information are the priority from the client at this stage.
Thursday | 2022-04-07 | 13:00 | 16:00 | 3 | Fixed some errors and technical issues [different computer version and tools] | Make sure all the progress are the same and all team members can run the code on their own computer | Stock info data are successfully collected from most popular indexes and were added to the database.
Friday | 2022-04-08 | 16:00 | 18:00 | 2 | Test before populating data to remote database | Completed part of client's requirements. | Some stock info werepopulated to the remote database.
Saturday | 2022-04-09 | 13:00 | 16:00 | 3 | Import some data and volume then populate in the database | Having some data and volume in the database for team members to move forward to meet clients' requirements. | Fixed some technical errors from imported data.
Sunday | 2022-04-10 | 12:00 | 14:00 | 2 | Weekly meeting[11th/2022] | Check the team member's progress,and we set weekly goals of each colleges we expected to be completed. Check if anyone needs assistance. | Every team members have their own contribution and understanding of this project
|  |  | Total | 20