## Week 12
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-05-30
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2022-05-30
Tuesday | 2022-05-31 | 9:00 | 15:00 | 6 | Adjusted get_weighted compound function | Not scheduled in the timeline | The function was able to compute weighted comp for stocks with price data less than 1 ytear (all stocks included)
Wednesday | 2022-06-01 | 15:00 | 17:00 | 2 | Weekly meeting, Code review and documentation | Prepare project for acceptance testing | Comments added to make code easier to understand. Code style updated for readability.
Thursday | 2022-06-02
Friday | 2022-06-03 | 15:00 | 20:00 | 5 | Refactor screening functionality. Run screening for past week. Allow relative strength updates between selected date | Improve usability of application by allowing dynamic screening conditions | Able to perform screening for different days using date as parameter. Able to calculate relative strength for specific day or between dates.
Saturday | 2022-06-04 | 13:00 | 18:00 | 5 | Test get_weighted compound on mulitple indexes | Not scheduled in the timeline | Completed without issues
Sunday | 2022-06-05 | 10:00 | 16:00 | 6 | Weekly meeting, Review, documentation and reproducability improvements. | Prepare project for acceptance testing | Sub systems integrated but not tested, Docker added to project, daily update improvements.
|  |  | Total | 24
Formulas:
Date = [Date, row above]+1

## Week 13
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-06-06
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2022-06-06
Tuesday | 2022-06-07
Wednesday | 2022-06-08 | 15:00 | 18:00 | 3 | Weekly meeting: Integrating codes into staging branch and testing | Scheduled on project timeline | Completed. Latest screening results are updated in order to prepare fundamental data
Thursday | 2022-06-09 | 11:00 | 12:00 | 1 | Consulting advisor on Poster and Demo presenation | To prepare for poster and demo presentation | Received feedbacks to adjust poster and plan for demo presentation
|  | 12:00 | 19:00 | 7 | Draft poster according to advisor's feedbacks | To prepare for demo presentation | Completed draft. To get feedbacks from team members
Friday | 2022-06-10 | 0:00 | 15:00 | 3 | Perform system tests from screening to getting fundamental data | To prepare for demo presentation | All issues solved
Saturday | 2022-06-11 | 11:00 | 13:00 | 2 | Client meeting: tets the application with client | Part of acceptance testing | There were issues setting up the app on the client's laptop
|  | 13:00 | 18:00 | 5 | Adjusted queries to get database status. Review CLI commands and added examples and additional descriptions | To prepare for demo presentation | Completed
Sunday | 2022-06-12 | 12:00 | 15:00 | 3 | Weekly meeting: Update database and review all codes before submission | Final check on everything on GitHub before submission | Completed update, review and submised all codes in Master branch
|  |  | Total | 24
Formulas:
Date = [Date, row above]+1

## Week 14
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-06-13
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2022-06-13
Tuesday | 2022-06-14
Wednesday | 2022-06-15 | 15:00 | 17:00 | 2 | Weekly meeting
Thursday | 2022-06-16
Friday | 2022-06-17
Saturday | 2022-06-18
Sunday | 2022-06-19 | 12:00 | 14:00 | 2 | Weekly meeting
|  |  | Total | 4
Formulas:
Date = [Date, row above]+1

## Template
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-02-28
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-02-28
Tuesday | 2022-03-01
Wednesday | 2022-03-02
Thursday | 2022-03-03
Friday | 2022-03-04
Saturday | 2022-03-05
Sunday | 2022-03-06
|  |  | Total | 0
Formulas:
Date = [Date, row above]+1

## Week 1
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  | a1829241 |  | Week starting: | 2022-02-28
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-02-28
Tuesday | 2022-03-01 | 14:00 | 15:00 | 1 | Study existing stock market screeners | Researching part of the project plan | Understand the nature and concepts of stock market screeners
Wednesday | 2022-03-02 | 13:00 | 15:00 | 2 | Team meeting (1/2022) | Prepare questions for client meeting | Meeting with client on 8 March 2022 via Zoom
Thursday | 2022-03-03 | 11:00 | 14:00 | 3 | Study on financial tools and concepts that can be used in stock screener | Create product features | Furthur study is required
Friday | 2022-03-04
Saturday | 2022-03-05
Sunday | 2022-03-06
|  |  | Total | 6
Formulas:
Date = [Date, row above]+1

## Week 2
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  | a1829241 |  | Week starting: | 2022-03-07
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-03-07 | 13:00 | 18:00 | 5 | Learn Python | Python will be used as main language for our backend | More understanding of Python
Tuesday | 2022-03-08 | 17:00 | 19:00 | 2 | Initial client meeting [1/2022] | Gives us an understanding of the project scope, requirements and deliverables | Decide on tech stack and design database for application
Wednesday | 2022-03-09 | 13:00 | 18:00 | 5 | Learn SQL and RDBMS | To prepare for team meeting for database setup | Understanding of basics of SQL and RDBMS
Thursday | 2022-03-10 | 17:00 | 19:00 | 2 | Team meeting via Zoom [2/2022] | Discuss on database setup, database design, backend technologies, API connection, etc. | Task allocation and expected completion dates set
Friday | 2022-03-11 | 13:00 | 18:00 | 5 | Setup database on Microsolf Azure and learn API | Database will be used for the project and API is used to pull data | Database with storage of 30GB is ready for the project
Saturday | 2022-03-12 | 13:00 | 15:00 | 2 | Team meeting via Zoom [3/2022] | Follow up on progress with allocated tasks | To update progress and discuss on solutions if there are any issues
Sunday | 2022-03-13
|  |  | Total | 21
Formulas:
Date = [Date, row above]+1

## Week 3
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  | a1829241 |  | Week starting: | 2022-03-14
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-03-14
Tuesday | 2022-03-15 | 17:00 | 19:00 | 2 | Team meeting on Project development and preparations for presentation [4/2022] | The meeting is expected to give a cleaer picture of the project outcome that matchs client's expectations | Get information of the expected result of the screener from the client
Wednesday | 2022-03-16 | 13:00 | 19:00 | 6 | Develop project features to get all stocks info from the database | Features are core parts that are used to screen stocks the get the expected result | All stocks can be exported from the database
Thursday | 2022-03-17 | 17:00 | 19:00 | 2 | Team meeting on combining draft presentation [5/2022] | The meeting is expected to keep all members on the same page and make progress in the same direction for the presenation | Draft version of ppt presentation
Friday | 2022-03-18 | 13:00 | 19:00 | 6 | Develop project features to screen stocks based on its size from the database | Features are core parts that are used to screen stocks the get the expected result | Stocks can be exported based on its size from the database
Saturday | 2022-03-19 | 17:00 | 19:00 | 2 | Team meeting on combining adjusted draft presentation and completing the final version; Follow up on project development | The meeting is expected to finalise details on presentation | Final version of ppt presentation
Sunday | 2022-03-20
|  |  | Total | 18
Formulas:
Date = [Date, row above]+1

## Week 4
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  | a1829241 |  | Week starting: | 2022-03-21
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-03-21 | 17:00 | 19:00 | 2 | Team meeting on Project development and preparations for presentation [6/2022] | Finalise details on the presentation and discuss progress on project development | Draft version of ppt presentation with 80% completion
Tuesday | 2022-03-22 | 17:00 | 19:00 | 2 | Team meeting on Project development and preparations for presentation | Finalise details on the presentation and discuss progress on project development | Draft version of ppt presentation with 80% completion
Wednesday | 2022-03-23 | 13:00 | 19:00 | 6 | Develop project features for investment themes | Features are core parts that are used to screen stocks for different investment strategies | A number of features to screen stocks
Thursday | 2022-03-24 | 17:00 | 19:00 | 2 | Team meeting on preparations for presentation and discuss on progress of project development [7/2022] | The meeting is expected to keep all members on the same page and make progress in the same direction for the presenation | Final version of ppt presentation
Friday | 2022-03-25 | 13:00 | 19:00 | 6 | Develop project features for investment themes | Features are core parts that are used to screen stocks for different investment strategies | A number of features to screen stocks
Saturday | 2022-03-26 | 17:00 | 21:00 | 4 | Develop project features for investment themes | Features are core parts that are used to screen stocks for different investment strategies | Testing features with database
Sunday | 2022-03-27
|  |  | Total | 22
Formulas:
Date = [Date, row above]+1

## Week 5
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  | a1829241 |  | Week starting: | 2022-03-28
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-03-28 | 16:00 | 17:00 | 1 | Record and submit presentation
Tuesday | 2022-03-29 | 9:00 | 15:00 | 6 | Work on database structure to reflect client's additional requirements | Database is a core part of the project and is being developed as planned | Working database that meets client's requirements
Wednesday | 2022-03-30 | 15:00 | 17:00 | 2 | Team weekly meeting [8/2022] | Update on project progress, set weekly goals of tasks expected to complete and solve any ongoing issues | Every member understands their role and on the same page for the project progress
Thursday | 2022-03-31 | 17:00 | 18:00 | 1 | Client meeting [2/2022] | Update on status database, project milestones, technical solution, q&a | Being on the same page with client regarding the developemnt of the project
Friday | 2022-04-01 | 11:00 | 17:00 | 6 | Work on screening functions as suggested by client | Being developed as planned, screening functions are considered important parts of the project | Working screening functions that reflect client's required criteria
Saturday | 2022-04-02 | 1:00 | 18:00 | 5 | Work on database structure to reflect client's additional requirements | Database is a core part of the project and is being developed as planned | Working database that meets client's requirements
Sunday | 2022-04-03 | 12:00 | 14:00 | 2 | Team weekly meeting [9/2022] | Update on project progress, check if allocated tasks are completed, set new goals | Project being developed to meet client's requirements
|  |  | Total | 21
Formulas:
Date = [Date, row above]+1

## Week 6
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  | a1829241 |  | Week starting: | 2022-04-04
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-04-04 | 16:00 | 18:00 | 2 | Review first draft of business case and draft plan | Allows team members improve assigned parts of business case and draft plan based on feedback. Synchronizes the team on project goals and deliverables. | Feedback on improvements to be made to assigned parts and plan for submission.
Tuesday | 2022-04-05 | 16:00 | 19:00 | 3 | Finalise draft plan, establish data pipeline to populate database with index and stock information | Prepare for submission of business case and draft plan. Work towards first deliverable for client | Business case and draft plan ready to submit. Data pipeline established and tested with different indexes
Wednesday | 2022-04-06 | 15:00 | 18:00 | 3 | Progress updates, task assignment and peer assistance. Implement and test population of local database with stock information | Ensures team members are making progress on assigned tasks and getting assistance if needed. Make progress on client deliverable | Team members reviewed code, researched and implemented functionality for populating database. Data pipeline improved with issues identified while getting index and stock information. Stock and Index information gathering aborted as this was taking longer than expected and was not a client priority at this stage.
Thursday | 2022-04-07 | 14:00 | 18:00 | 4 | Implement flexible code to populate local database with stock prices from various indexes | Final step before populating remote database to present to client | Stock price data successfully gathered for most popular indexes and added to local database. Multiple table naming issues identified and fixed. Stock symbol prefixes noted and added.
Friday | 2022-04-08 | 11:00 | 13:00 | 2 | Final testing before populating remote database | Gets the team closer to completing client deliverable of populated database | Some stocks from major indexes populated on remote database
Saturday | 2022-04-09 | 11:00 | 16:00 | 5 | Import technical data and volume and populate in the database | Having technical data and volume will allow team to move towards fulfiling clien's requirements | Had technical issues to import data
Sunday | 2022-04-10 | 12:00 | 13:00 | 2 | Progress updates, task assignment and peer assistance | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Client deliverable progress reviewed, tasks assigned
|  |  | Total | 21
Formulas:
Date = [Date, row above]+1

## Week 6.1
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-04-11
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-04-11
Tuesday | 2022-04-12 | 10:00 | 15:00 | 5 | Test TA-Lib for comparing sma and volume | Getting sma and volume would be considered a key progress for the project | TA-Lib liabiary is not suitable for the implementation
Wednesday | 2022-04-13 | 15:00 | 17:00 | 2 | Progress updates, task assignment and peer assistance. Discusse issues regarding getting price data for stocks in NYSE composite. Also, implementation on sma and volume | Ensures team members are making progress on assigned tasks and getting assistance if needed. Solves issues that make cause project delay. | All team members were on the same page on the progress of all assigned tasks and some issues were discussed and solved including getting sma and volume by using pandas_ta instead of TA-Lib.
Thursday | 2022-04-14 | 13:00 | 17:00 | 4 | Write sql select query to load close price and volume from database and convert them into pandas dataframe | Getting sma and volume would be considered a key progress for the project | sql query to select price data for different required periods were completed
Friday | 2022-04-15 | 12:00 | 17:00 | 5 | Write a code to implement sma and volume using pandas_ta | Getting sma and volume would be considered a key progress for the project | Functions to get sma and volume for different required periods were completed
Saturday | 2022-04-16 | 14:00 | 19:00 | 5 | Write sql update query to insert sma and volume into existing price tables | Update sma and volume into database can facilitate technical analysus in the next steps | Update query was not fully completed and needed assistance from Joseph to help check the coding
Sunday | 2022-04-17
|  |  | Total | 21
Formulas:
Date = [Date, row above]+1

## Week 6.2
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-04-18
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2022-04-18 | 12:00 | 13:00 | 1 | Update on project progress in the following areas: data assurance, implementation of technical analysis and acquisition plan on fundamental data | Regular update helps team stay active and make progress as planned | Team members understood the implementation of data assurance for delisted stocks and functions to get relative strength and relative rating
|  | 14:00 | 18:00 | 4 | Adjust coding for implementing relative strength and relative rating based on feedbacks from team members | Progress was made as planned | Functions to implement relative strength and rating were completed
Tuesday | 2022-04-19 | 13:00 | 13:30 | 0.5 | Small team meeting to update progress and discuss issues | Team members help solve problems and make progress together | Some technical issues were solved
|  | 10:00 | 16:00 | 6 | Test relative strength functions with major indexes | To ensure functions are capable of running a bigger scale of data to avoid delays from code revisions | Found problems when implementing functions for relative strength with major indexes i.e. Nasdaq
Wednesday | 2022-04-20 | 15:00 | 16:00 | 1 | Regular weekly meeting to discuss the progress, the status and the plan of each team member's assigned tasks. Plan on meeting client next week | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Team members understood the status of each other's assigned tasks and the targets expected to achieve before meeting with the client
Thursday | 2022-04-21 | 17:00 | 18:00 | 1 | Client reviews database and implementation of RSI | Client can help validate the progress being made is aligned with the requirements
Friday | 2022-04-22 | 13:00 | 17:00 | 5 | Adjust coding according to client's feedbacks | Database application can be implemented as required by the client and potential delays are avoided
Saturday | 2022-04-23 | 12:00 | 17:00 | 5 | Update database with sma, volume, rsi, 52w hign, 52w low | Having all the mentioned items updated into database will be considered a significant progress for the first set of client's requirements
Sunday | 2022-04-24 | 12:00 | 13:00 | 1 | Progress updates, task assignment and peer assistance | Ensures team members are making progress on assigned tasks and getting assistance if needed.
|  |  | Total | 24.5
Formulas:
Date = [Date, row above]+1

## Week 7
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-04-25
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-04-25 | 23:00 | 16:00 | 5 | Add get_dates function to return a set of start and end dates for the last 4 quarters | Part of the conditions to screen stocks in the plan | Completed
Tuesday | 2022-04-26 | 13:00 | 17:00 | 4 | Adjust get_comprod with get_dates to return a more accurate result of compound value | Part of the conditions to screen stocks in the plan | Appending to fix datetime errors
Wednesday | 2022-04-27 | 15:00 | 17:00 | 2 | Weekly meeting | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Milestone 1 draft completion was scheduled for next meeting. Fundamental data sourcing and storage was discussed and solutions decided.
Thursday | 2022-04-28 | 13:00 | 17:00 | 4 | Adjust get_comprod with get_dates to return a more accurate result of compound value | Part of the conditions to screen stocks in the plan | Completed
Friday | 2022-04-29 | 12:00 | 17:00 | 5 | Test get_compound with index prices and make adjustments if needed | Part of the conditions to screen stocks in the plan | Completed
Saturday | 2022-04-30
Sunday | 2022-05-01 | 12:00 | 14:00 | 2 | Weekly meeting | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Milestone 1 draft was completed. Fundamental data fetching was found to be progressing well.
|  |  | Total | 22
Formulas:
Date = [Date, row above]+1

## Week 8
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-05-02
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2022-05-02 | 13:00 | 17:00 | 4 | Write a function to get relative strength from weighted comp of stock and weighted comp of index | Part of the conditions to screen stocks in the plan | Completed
Tuesday | 2022-05-03 | 14:00 | 17:00 | 3 | Adjust relative_strength function for flexibility in using stock_update | Part of the conditions to screen stocks in the plan | Working but there are some errors with the results
Wednesday | 2022-05-04 | 15:00 | 17:00 | 2 | Weekly meeting | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Added additional fundamental data. Prepared questions and draft on milestone 1 report to get feedbacks in the workshop
Thursday | 2022-05-05 | 18:30 | 19:30 | 1 | Client meeting [4/2022] | Update the status of the project with client before testing | Client gave feedbacks on adding relative_strength_sp500 for all stocks and reviewed the status on acquiring fundamental data
Friday | 2022-05-06 | 13:00 | 17:00 | 4 | Test screening queries with all indexes and fix errors if any | According to the plan and on schedule | Working in progress
Saturday | 2022-05-07 | 13:00 | 17:00 | 4 | Plan on data virtualisation for price data | According to the plan and on schedule | To be further discussed in team meeting
Sunday | 2022-05-08 | 12:00 | 14:00 | 2 | Weekly meeting | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Reflected feedbacks on milestone 1 report and finalised the details. Discussed and shared ideas on testing plan
|  |  | Total | 20
Formulas:
Date = [Date, row above]+1

## Week 9
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-05-09
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2022-05-09 | 13:00 | 17:00 | 4 | Draft final milestone report | According to the plan and on schedule | Completed
Tuesday | 2022-05-10 | 10:00 | 14:00 | 4 | Adjust weighted_comp to improve the speed of screening | Additional task added into the project development plan | Completed
Wednesday | 2022-05-11 | 15:00 | 17:00 | 2 | Weekly meeting | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Completed daily dataset queries and finalised details on the final milestone report
Thursday | 2022-05-12 | 10:00 | 14:00 | 4 | Work on getting the rank for all stocks as requested by the client | Additional task added into the project development plan | Work in progress
Friday | 2022-05-13 | 15:00 | 17:00 | 2 | Final review of final milestone report before submission | According to the plan and on schedule | Final milestone report was well submitted
Saturday | 2022-05-14
Sunday | 2022-05-15 | 12:00 | 14:00 | 2 | Weekly meeting | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Tasks on testing plan report were allocated. Updated print function for fundamental data. Updated progress on testing plan report
|  |  | Total | 18
Formulas:
Date = [Date, row above]+1

## Week 10
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-05-16
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-05-16 | 13:00 | 17:00 | 4 | Study testing tools such unittest and pandas testing | Part of the testing as planned | Gained skills and knowledge required to implement unit testing
Tuesday | 2022-05-17 | 13:00 | 17:00 | 4 | Draft testing plan report | Part of the testing as planned | Draft of testing plan report was completed
Wednesday | 2022-05-18 | 15:00 | 17:00 | 2 | Weekly meeting | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Summarised unit testing results and sent some screening results to the client to check the accuracy compared wih the client's dataset.
Thursday | 2022-05-19 | 13:00 | 17:00 | 4 | Write test scripts for unit testing | Part of the testing as planned | Completed
Friday | 2022-05-20 | 13:00 | 17:00 | 4 | Update testing plan report with unit testing results | Part of the testing as planned | Draft of testing plan report was updated (testing results added in the appendix)
Saturday | 2022-05-21 | 13:00 | 17:00 | 4 | Study Pytest as a testing tool for integration testing | Part of the testing as planned | Gained skills and knowledge required to implement integration and system testing
Sunday | 2022-05-22 | 12:00 | 14:00 | 2 | Weekly meeting | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Finalised details on the planning report and adjusted the format before submission. Prepared a dataset requested by the client for testing the screen results.
|  |  | Total | 24
Formulas:
Date = [Date, row above]+1

## Week 11
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-05-23
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2022-05-23 | 13:00 | 16:00 | 3 | Summarise unit testing results in the testing plan report | Part of the testing as planned | Completed
Tuesday | 2022-05-24 | 17:00 | 19:00 | 2 | Final review on testing plan report before submission | Testing report is submitted as scheduled | Testing plan report was well submiited
Wednesday | 2022-05-25 | 15:00 | 17:00 | 2 | Weekly meeting:Discuss on test report, preparation for the poster, demo and plan for presentation | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Tasks on poster and demo were allocated
Thursday | 2022-05-26 | 13:00 | 17:00 | 4 | Work on allocated tasks on poster: Methodologies | This task is according to the plan and on the schedule
|  | 17:00 | 19:30 | 2.5 | Urgent client meeting on technical issues | This meeting was not scheduled | Some issues were solved and clarifications on pending requirements were given
Friday | 2022-05-27 | 11:00 | 15:00 | 4 | Work on data integrity testing as part of data assurance | As part of the testing plan as scheduled
Saturday | 2022-05-28 | 11:00 | 16:00 | 5 | Continue to work on data integrity testing as part of data assurance | As part of the testing plan as scheduled
Sunday | 2022-05-29 | 12:00 | 14:00 | 2 | Weekly meeting | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Update progress of testing with the client. Summarised all the testing results and discuss plan to prepare a full test report. Update on progress on the poster assignment.
|  |  | Total | 24.5
Formulas:
Date = [Date, row above]+1