## Template
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-02-28
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-02-28
Tuesday | 2022-03-01
Wednesday | 2022-03-02
Thursday | 2022-03-03
Friday | 2022-03-04
Saturday | 2022-03-05
Sunday | 2022-03-06
|  |  | Total | 0
Formulas:
Date = [Date, row above]+1

## Week 1
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-02-28
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-02-28
Tuesday | 2022-03-01
Wednesday | 2022-03-02 | 13:00 | 15:00 | 2 | Team meeting (1/2022) | Prepare questions for client meeting | Meeting with client on 8 March 2022 via Zoom
Thursday | 2022-03-03
Friday | 2022-03-04
Saturday | 2022-03-05
Sunday | 2022-03-06
|  |  | Total | 2
Formulas:
Date = [Date, row above]+1

## Week 2
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-03-07
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-03-07
Tuesday | 2022-03-08 | 17:00 | 19:00 | 2 | Initial client meeting [1/2022] | Gives us an understanding of the project scope, requirements and deliverables | Decide on tech stack and design database for application
Wednesday | 2022-03-09
Thursday | 2022-03-10 | 17:00 | 19:00 | 2 | Team meeting via Zoom [2/2022] | Discuss on database setup, database design, backend technologies, API connection, etc. | Task allocation and expected completion dates set
Friday | 2022-03-11
Saturday | 2022-03-12 | 13:00 | 15:00 | 2 | Team meeting via Zoom [3/2022] | Follow up on progress with allocated tasks | To update progress and discuss on solutions if there are any issues
Sunday | 2022-03-13
|  |  | Total | 6
Formulas:
Date = [Date, row above]+1

## Week 3
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-03-14
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-03-14
Tuesday | 2022-03-15 | 17:00 | 19:00 | 2 | Team meeting on Project development and preparations for presentation [4/2022] | The meeting is expected to give a cleaer picture of the project outcome that matchs client's expectations | Get information of the expected result of the screener from the client
Wednesday | 2022-03-16
Thursday | 2022-03-17 | 17:00 | 19:00 | 2 | Team meeting on combining draft presentation [5/2022] | The meeting is expected to keep all members on the same page and make progress in the same direction for the presenation | Draft version of ppt presentation
Friday | 2022-03-18
Saturday | 2022-03-19
Sunday | 2022-03-20
|  |  | Total | 4
Formulas:
Date = [Date, row above]+1

## Week 4
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-03-21
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-03-21 | 17:00 | 19:00 | 2 | Team meeting on Project development and preparations for presentation [6/2022] | Finalise details on the presentation and discuss progress on project development | Draft version of ppt presentation with 80% completion
Tuesday | 2022-03-22
Wednesday | 2022-03-23
Thursday | 2022-03-24 | 17:00 | 19:00 | 2 | Team meeting on preparations for presentation and discuss on progress of project development [7/2022] | The meeting is expected to keep all members on the same page and make progress in the same direction for the presenation | Final version of ppt presentation
Friday | 2022-03-25 | 14:00 | 15:00 | 1 | Presentation Practice #1 | To see the flow of presentation and review each other for the content | Understand transition between each member
Saturday | 2022-03-26
Sunday | 2022-03-27 | 15:00 | 16:00 | 1 | Presentation Practice #2 with Recording | Review each other for the content and transition before recording presentation | Know where to improve before recording presentation
|  |  | Total | 6
Formulas:
Date = [Date, row above]+1

## Week 5
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-03-28
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-03-28 | 16:00 | 17:00 | 1 | Record and submit presentation
Tuesday | 2022-03-29
Wednesday | 2022-03-30 | 15:00 | 17:00 | 2 | Team weekly meeting [8/2022] | Update on project progress, set weekly goals of tasks expected to complete and solve any ongoing issues | Every member understands their role and on the same page for the project progress
Thursday | 2022-03-31 | 17:00 | 18:00 | 1 | Client meeting [2/2022] | Update on status database, project milestones, technical solution, q&a | Being on the same page with client regarding the developemnt of the project
Friday | 2022-04-01
Saturday | 2022-04-02
Sunday | 2022-04-03 | 12:00 | 14:00 | 2 | Team weekly meeting [9/2022] | Update on project progress, check if allocated tasks are completed, set new goals | Project being developed to meet client's requirements
|  |  | Total | 6
Formulas:
Date = [Date, row above]+1

## Week 6
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-04-04
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-04-04 | 16:00 | 18:00 | 2 | Review first draft of business case and draft plan | Allows team members improve assigned parts of business case and draft plan based on feedback. Synchronizes the team on project goals and deliverables. | Feedback on improvements to be made to assigned parts and plan for submission.
Tuesday | 2022-04-05 | 16:00 | 19:00 | 3 | Finalise draft plan, establish data pipeline to populate database with index and stock information | Prepare for submission of business case and draft plan. Work towards first deliverable for client | Business case and draft plan ready to submit. Data pipeline established and tested with different indexes
Wednesday | 2022-04-06 | 15:00 | 18:00 | 3 | Progress updates, task assignment and peer assistance. Implement and test population of local database with stock information | Ensures team members are making progress on assigned tasks and getting assistance if needed. Make progress on client deliverable | Team members reviewed code, researched and implemented functionality for populating database. Data pipeline improved with issues identified while getting index and stock information. Stock and Index information gathering aborted as this was taking longer than expected and was not a client priority at this stage.
Thursday | 2022-04-07 | 14:00 | 18:00 | 4 | Implement flexible code to populate local database with stock prices from various indexes | Final step before populating remote database to present to client | Stock price data successfully gathered for most popular indexes and added to local database. Multiple table naming issues identified and fixed. Stock symbol prefixes noted and added.
Friday | 2022-04-08 | 11:00 | 13:00 | 2 | Final testing before populating remote database | Gets the team closer to completing client deliverable of populated database | Some stocks from major indexes populated on remote database
Saturday | 2022-04-09
Sunday | 2022-04-10 | 12:00 | 13:00 | 1 | Progress updates, task assignment and peer assistance | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Client deliverable progress reviewed, tasks assigned
|  |  | Total | 15
Formulas:
Date = [Date, row above]+1

## Week 6.1
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-04-11
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-04-11
Tuesday | 2022-04-12
Wednesday | 2022-04-13 | 15:00 | 17:00 | 2 | Progress updates, task assignment and peer assistance. Discusse issues regarding getting price data for stocks in NYSE composite. Also, implementation on sma and volume | Ensures team members are making progress on assigned tasks and getting assistance if needed. Solves issues that make cause project delay. | All team members were on the same page on the progress of all assigned tasks and some issues were discussed and solved including getting sma and volume by using pandas_ta instead of TA-Lib.
Thursday | 2022-04-14
Friday | 2022-04-15
Saturday | 2022-04-16
Sunday | 2022-04-17
|  |  | Total | 2
Formulas:
Date = [Date, row above]+1

## Week 6.2
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-04-18
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2022-04-18 | 12:00 | 13:00 | 1 | Update on project progress in the following areas: data assurance, implementation of technical analysis and acquisition plan on fundamental data | Regular update helps team stay active and make progress as planned | Team members understood the implementation of data assurance for delisted stocks and functions to get relative strength and relative rating
Tuesday | 2022-04-19 | 13:00 | 13:30 | 0.5 | Small team meeting to update progress and discuss issues | Team members help solve problems and make progress together | Some technical issues were solved
Wednesday | 2022-04-20 | 15:00 | 16:00 | 2 | Regular weekly meeting to discuss the progress, the status and the plan of each team member's assigned tasks. Plan on meeting client next week | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Team members understood the status of each other's assigned tasks and the targets expected to achieve before meeting with the client
Thursday | 2022-04-21 | 17:00 | 18:00 | 1 | Client reviews database and implementation of RSI | Client can help validate the progress being made is aligned with the requirements
Friday | 2022-04-22
Saturday | 2022-04-23
Sunday | 2022-04-24 | 12:00 | 13:30 | 1.5 | Progress updates, task assignment and peer assistance | Ensures team members are making progress on assigned tasks and getting assistance if needed.
|  |  | Total | 6
Formulas:
Date = [Date, row above]+1

## Week 7
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-04-25
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-04-25
Tuesday | 2022-04-26
Wednesday | 2022-04-27 | 15:00 | 17:00 | 2 | Weekly meeting | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Milestone 1 draft completion was scheduled for next meeting. Fundamental data sourcing and storage was discussed and solutions decided.
Thursday | 2022-04-28
Friday | 2022-04-29
Saturday | 2022-04-30
Sunday | 2022-05-01 | 12:00 | 14:00 | 2 | Weekly meeting | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Milestone 1 draft was completed. Fundamental data fetching was found to be progressing well.
|  |  | Total | 4
Formulas:
Date = [Date, row above]+1

## Week 8
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-05-02
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2022-05-02
Tuesday | 2022-05-03
Wednesday | 2022-05-04 | 15:00 | 17:00 | 2 | Weekly meeting | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Added additional fundamental data. Prepared questions and draft on milestone 1 report to get feedbacks in the workshop
Thursday | 2022-05-05 | 18:30 | 19:30 | 1 | Client meeting [4/2022] | Update the status of the project with client before testing | Client gave feedbacks on adding relative_strength_sp500 for all stocks and reviewed the status on acquiring fundamental data
Friday | 2022-05-06
Saturday | 2022-05-07
Sunday | 2022-05-08 | 12:00 | 14:00 | 2 | Weekly meeting | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Reflected feedbacks on milestone 1 report and finalised the details. Discussed and shared ideas on testing plan
|  |  | Total | 5
Formulas:
Date = [Date, row above]+1

## Week 9
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-05-09
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2022-05-09
Tuesday | 2022-05-10
Wednesday | 2022-05-11 | 15:00 | 17:00 | 2 | Weekly meeting | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Completed daily dataset queries and finalised details on the final milestone report
Thursday | 2022-05-12
Friday | 2022-05-13 | 15:00 | 17:00 | 2 | Final review of final milestone report before submission | According to the plan and on schedule | Final milestone report was well submitted
Saturday | 2022-05-14
Sunday | 2022-05-15 | 12:00 | 14:00 | 2 | Weekly meeting | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Tasks on testing plan report were allocated. Updated print function for fundamental data. Updated progress on testing plan report
|  |  | Total | 6
Formulas:
Date = [Date, row above]+1

## Week 10
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-05-16
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-05-16
Tuesday | 2022-05-17
Wednesday | 2022-05-18 | 15:00 | 17:00 | 2 | Weekly meeting | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Summarised unit testing results and sent some screening results to the client to check the accuracy compared wih the client's dataset.
Thursday | 2022-05-19
Friday | 2022-05-20
Saturday | 2022-05-21
Sunday | 2022-05-22 | 12:00 | 14:00 | 2 | Weekly meeting | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Finalised details on the planning report and adjusted the format before submission. Prepared a dataset requested by the client for testing the screen results.
|  |  | Total | 4
Formulas:
Date = [Date, row above]+1

## Week 11
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-05-23
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2022-05-23
Tuesday | 2022-05-24 | 17:00 | 19:00 | 2 | Final review on testing plan report before submission | Testing report is submitted as scheduled | Testing plan report was well submiited
Wednesday | 2022-05-25 | 15:00 | 17:00 | 2 | Weekly meeting:Discuss on test report, preparation for the poster, demo and plan for presentation | Ensures team members are making progress on assigned tasks and getting assistance if needed. | Tasks on poster and demo were allocated
Thursday | 2022-05-26
Friday | 2022-05-27
Saturday | 2022-05-28
Sunday | 2022-05-29 | 12:00 | 14:00 | 2 | Weekly meeting | Ensures team members are making progress on assigned tasks and getting assistance if needed.
|  |  | Total | 6
Formulas:
Date = [Date, row above]+1

## Week 12
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-05-30
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2022-05-30
Tuesday | 2022-05-31
Wednesday | 2022-06-01 | 15:00 | 18:00 | 3 | Weekly meeting: Integrating codes into staging branch and testing | Scheduled on project timeline | Completed. Latest screening results are updated in order to prepare fundamental data
Thursday | 2022-06-02
Friday | 2022-06-03 | 15:00 | 20:00 | 5 | Refactor screening functionality. Run screening for past week. Allow relative strength updates between selected date | Improve usability of application by allowing dynamic screening conditions | Able to perform screening for different days using date as parameter. Able to calculate relative strength for specific day or between dates.
Saturday | 2022-06-04 | 0:00 | 15:00 | 3 | Perform system tests from screening to getting fundamental data | To prepare for demo presentation
Sunday | 2022-06-05 | 10:00 | 16:00 | 6 | Weekly meeting, Review, documentation and reproducability improvements. | Prepare project for acceptance testing | Sub systems integrated but not tested, Docker added to project, daily update improvements.
|  |  | Total | 17
Formulas:
Date = [Date, row above]+1

## Week 13
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-06-06
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2022-06-06
Tuesday | 2022-06-07
Wednesday | 2022-06-08 | 15:00 | 18:00 | 3 | Weekly meeting: Integrating codes into staging branch and testing | Scheduled on project timeline | Completed. Latest screening results are updated in order to prepare fundamental data
Thursday | 2022-06-09 | 11:00 | 12:00 | 1 | Consulting advisor on Poster and Demo presenation | To prepare for poster and demo presentation | Received feedbacks to adjust poster and plan for demo presentation
Friday | 2022-06-10 | 0:00 | 15:00 | 3 | Perform system tests from screening to getting fundamental data | To prepare for demo presentation
Saturday | 2022-06-11
Sunday | 2022-06-12 | 12:00 | Total | 7 | Weekly meeting: Review all codes before submission | Scheduled on project timeline
|  |  | Total | 14
Formulas:
Date = [Date, row above]+1

## Week 14
MCI Project Weekly Time Sheet
Team | 17 | Student ID |  |  |  | Week starting: | 2022-06-13
Day | Date | Time In | Time Out | Total hours | Task | How does it fit to project plan? | Outcome/Next action
Monday | 2022-06-13
Tuesday | 2022-06-14
Wednesday | 2022-06-15 | 15:00 | 18:00 | 3 | Weekly meeting: Integrating codes into staging branch and testing
Thursday | 2022-06-16
Friday | 2022-06-17
Saturday | 2022-06-18
Sunday | 2022-06-19 | 12:00 | 14:00 | 2 | Weekly meeting
|  |  | Total | 5
Formulas:
Date = [Date, row above]+1